## Estimate
Project Name: |  | Elderly Health Monitoring and Alert System
Module Name: |  | Sprint 1
Development Team: |  | C1SE.40
Start Date: |  | 3/9/02025
End Date: |  | 2025-01-10
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Thang | Huỳnh Minh Thắng | 51 |  |  |  | Early
2 | Dung | Mai Văn Dũng | 17 |  |  |  | Unfinished
3 | Cuong | Trương Mạnh Cường | 21
4 | Khoa | Nguyễn Khắc Nguyên Khoa | 26
5 | Duy | Võ Lê Duy | 30
Total |  |  | 145
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01
| Sprint Plan Meeting |  | All member | 6 | 0
| Create Sprint Backlog for Sprint 1 |  | Duy | 6 | 0
| Create Test Plan document for Sprint 1 |  | Thang | 7 | 2 | 0
Design UI
| UI Log in |  | Khoa | 3 | 3 | 0
| UI Registration |  | Khoa | 1 | 1 | 0
| UI Verify OTP |  | Khoa | 1 | 1 | 0
| UI forgot password |  | Cuong | 1 | 1 | 1 | 0
| UI homepage |  | Thang | 1 |  | 1
| UI blood pressure |  | Khoa | 2 | 2 | 2 | 0
| UI dashboard (web) |  | Dung | 3 | 3 | 3 | 0
| UI lifystyle |  | Dung | 2 | 2 | 2 | 0
| UI setting |  | Cuong | 2 | 2 | 2 | 2 | 0
Coding
| (Front-end) home page |  | Khoa | 5 | [5 empty] | 5 | 3 | 1 | 0
| (Front-end) registration |  | Khoa | 5 | [5 empty] | 5 | 3 | 1 | 0
| (Front-end) log in |  | Cuong | 5 | [5 empty] | 5 | 3 | 1 | 0
| (Front-end) forgot password |  | Cuong | 4 | [8 empty] | 4 | 2 | 2 | 2 | 0
| (Front-end) Verify OTP |  | Khoa | 4 | [8 empty] | 4 | 2 | 2 | 2 | 0 |  | 0
| (Front-end) blood pressure |  | Khoa | 5 | [9 empty] | 5 | 5 | 5 | 3 | 1
| (Front-end) dashboard (web) |  | Dung | 5 | [5 empty] | 5 | 3 | 1 | 0
| (Front-end) lifystyle |  | Dung | 5 | [8 empty] | 5 | 3 | 3 | 3 | 1 | 0
| (Front-end) setting |  | Cuong | 5 | [9 empty] | 5 | 5 | 5 | 3 | 1 | 0
| (Back-end) registration |  | Thang | 6 | [5 empty] | 6 | 4 | 2 | 0
| (Back-end) log in |  | Thang | 6 | [5 empty] | 6 | 4 | 2 | 0
| (Back-end) forgot password |  | Thang | 4 | [8 empty] | 4 | 2 | 2 | 2 | 0
| (Back-end) Verify OTP |  | Duy | 4 | [15 empty] | 4 | 2 | 2 | 2 | 0
| (Back-end) setting |  | Duy | 6 | [20 empty] | 6 | 4 | 2 | 0
| (Back-end) skeleton recognition function |  | Duy | 14 | [25 empty] | 14 | 10 | 7 | 6
Testing and fix bug
| Design Test Case for home page |  | Thang | 2 | [13 empty] | 2 | 1 | 0
| Design Test Case for registration |  | Thang | 2 | [13 empty] | 2 | 1 | 0
| Design Test Case for log in |  | Thang | 2 | [14 empty] | 2 | 1 | 0
| Design Test Case for forgot password |  | Thang | 2 | [14 empty] | 2 | 1 | 0
| Design Test Case for Verify OTP |  | Thang | 2 | [15 empty] | 2 | 1 | 0
| Design Test Case for blood pressure |  | Thang | 2 | [15 empty] | 2 | 2 | 1 | 0
| Design Test Case for dashboard (web) |  | Dung | 2 | [15 empty] | 2 | 1 | 0
| Design Test Case for lifystyle |  | Cuong | 2 | [17 empty] | 2 | 1 | 0
| Design Test Case for setting |  | Cuong | 2 | [17 empty] | 2 | 1 | 0
Fix Bug & Release Sprint 1
| Implement test case |  | All member | 8 | [18 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Fix bugs and report |  | All member | 20 | [18 empty] | 20 | 20 | 20 | 20 | 20 | 16 | 12 | 12 | 8 | 4 | 2
| Retest |  | All member | 10 | [18 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0
| Closing |  | All member | 2 | [18 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  |  | TOTAL | 176 | 17 | 11 | 2 | 0 | 0 | 32 | 20 | 8 | 17 | 19 | 19 | 19 | 7 | 6 | 6 | 12 | 6 | 7 | 44 | 40 | 46 | 44 | 42 | 36 | 32 | 42 | 28 | 17 | 0

## Actual
Project Name: |  | LEARNING ENGLISH TOGETHER
Module Name: |  | Sprint 1
Development Team: |  | C2SE.12
Start Date: |  | 15/3/2021
End Date: |  | 2021-12-04
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Ha | Lê Thanh Hà | 40 | 41 |  |  | Early
2 | Hieu | Lê Xuân Hiếu | 42 | 43 |  |  | Unfinished
3 | My | Ngô Ngọc Mỹ | 41 | 41
4 | Thong | Đoàn Trung Thông | 44 | 44
Total |  |  | 167 | 169
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Actual | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-27 | 2021-03-28 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14
| Sprint Plan Meeting |  | All member | 4 | 0
| Create Sprint Backlog for Sprint 1 |  | Ha | 3 | 0
| Create Test Plan document for Sprint 1 |  | Ha | 2 | 2 | 0
Design UI
| UI home page |  | Hieu | 4 | 3 | 1 | 0
| UI registration |  | Ha | 1 | 1 | 0
| UI log in |  | Ha | 1 | 1 | 0
| UI forgot password |  | Ha | 1 | 1 | 1 | 0
| UI profile user |  | Hieu | 2 | 2 | 2 | 0
| UI chat room group |  | Ha | 3 | 3 | 3 | 0
| UI list group |  | Hieu | 2 | 2 | 0
| UI member group |  | Ha | 2 | 2 | 2 | 2 | 0
| UI call video group |  | Hieu | 2 | 2 | 2 | 2 | 0
| UI record group |  | Ha | 2 | 2 | 2 | 0
| UI meessager |  | Hieu | 3 | 3 | 3 | 3 | 3 | 0
Database
| Design database |  | Thong | 4 | 4 | 4 | 4 | 4 | 0
Coding
| (Front-end) home page |  | Hieu, Ha | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 0
| (Front-end) registration |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) log in |  | Ha | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) forgot password |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) profile user |  | Hieu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) chat room group |  | Hieu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) list group |  | Ha | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) member group |  | Hieu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) call video group |  | Hieu, Ha | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
| (Front-end) record group |  | Ha | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) meessager |  | Hieu | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) registration |  | My | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) log in |  | My | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) forgot password |  | My | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) profile user |  | Thong | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| (Back-end) chat room group |  | Thong, My | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0
| (Back-end) list group |  | Thong | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 0
| (Back-end) member group |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Back-end) call video group |  | Thong, My | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 0
| (Back-end) record group |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Back-end) meessager |  | Thong | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 0
Testing and fix bug
| Design Test Case for registration |  | My | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for log in |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for forgot password |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for profile user |  | My | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for chat room group |  | Hieu | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design Test Case for list group |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for member group |  | Hieu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for call video group |  | Hieu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for record group |  | Ha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design Test Case for meessager |  | Hieu | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Fix Bug & Release Sprint 1
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18 | 16 | 14 | 12 | 9 | 7 | 5 | 2 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 7 | 5 | 3 | 2 | 1 | 1 | 1 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 169 | 158 | 152 | 143 | 139 | 132 | 130 | 117 | 110 | 106 | 98 | 94 | 87 | 80 | 76 | 74 | 66 | 59 | 50 | 42 | 36 | 32 | 30 | 27 | 23 | 19 | 14 | 11 | 8 | 5 | 3 | 0

## Chart
Burn down chart Sprint 1
Estimate | Actual | Date
158 | 158 | 2021-03-15
153 | 152 | 2021-03-16
145 | 143 | 2021-03-17
139 | 139 | 2021-03-18
132 | 132 | 2021-03-19
126 | 130 | 2021-03-20
118 | 117 | 2021-03-21
110 | 110 | 2021-03-22
104 | 106 | 2021-03-23
98 | 98 | 2021-03-24
92 | 94 | 2021-03-25
86 | 87 | 2021-03-26
80 | 80 | 2021-03-27
74 | 76 | 2021-03-28
66 | 74 | 2021-03-29
60 | 66 | 2021-03-30
55 | 59 | 2021-03-31
50 | 50 | 2021-04-01
43 | 42 | 2021-04-02
36 | 36 | 2021-04-03
32 | 32 | 2021-04-04
27 | 30 | 2021-04-05
22 | 27 | 2021-04-06
16 | 23 | 2021-04-07
12 | 19 | 2021-04-08
8 | 14 | 2021-04-09
6 | 11 | 2021-04-10
3 | 8 | 2021-04-11
0 | 5 | 2021-04-12
| 3 | 2021-04-13
| 0 | 2021-04-14