## Main
Scrum Project
Product
Active versions
Team |  |  | Product Owner
Scrum Master |  |  | Other Stakeholders
Developers
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2019-01-07 | 2019-01-18 | Complete | 3
[6 empty] | 2 | 2019-01-21 | 2019-02-01 | Complete | 25
[6 empty] | 3 | 2019-02-04 | 2019-02-15 | Complete | 20
[6 empty] | 4 | 2019-02-18 | 2019-03-01 | Complete | 25
[6 empty] | 5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register | Personal User | Create an account | I can login with my own account to access the website | - Username must not contain spaces and not be accented - Password must be > 8 characters, < 16 characters include uppercase letters, lowercase letters, numbers and special characters. |  | 3 |  |  |  | 1 | 30
PB02 | Login | Personal User | Login to website | I can see all the post about thieves and robberies | - Login with facebook and gmail - Input data to enter: + Username accepted + Password accepted |  | 3 |  |  |  | 1 | 35
PB03 | Log out | Personal User | Log out from the currently account | I can exit my account whenever I want | - Click the "log out" button - Exit from the currently account |  | 3 |  |  |  | 1 | 25
PB04 | Forgot password | Personal User | Recover password when forgot | I can change my password into the new one and get my account back | - Click "Forgot password" button - Use the link sent to the account's email which registered in profile to change the new password |  | 3 |  |  |  | 1 | 30
PB05 | Send verify account request | Personal User | Verify the account | My account can look more reputable | - Click "Send verify" button - Send photos of user's ID Card in both side - Send picture of user's face |  | 1 |  |  |  | 3 | 90
PB06 | Edit profile | Personal User | Edit my public profile | I can edit my personal information | - Allow users to edit any personal information they want |  | 3 |  |  |  | 1 | 30
PB07 | Create a post | Personal User | Create a post | I can post whatever I need | - This allows users to create an article and post what they need - Don't support sensitive, hostile language |  | 2 |  |  |  | 1 | 40
PB08 | Edit the post | Personal User | Edit the post | I can modify the content of my posts | - This enables users to modify the content of the article they wish to modify. - Don't support sensitive, hostile language |  | 2 |  |  |  | 1 | 40
PB09 | Delete the post | Personal User | Delete the post | I can delete my post | - This allow the user delete their post |  | 3 |  |  |  | 1 | 30
PB10 | Interact with posts | Personal User | Interact with posts | I can interact with other people's posts | -This allows users to interact with the posts of other individuals. - Click "Like" button below the post - Click "Share" button below the post - Add Comment in comment field of post |  | 2 |  |  |  | 2 | 40
PB11 | View posts interaction history | Personal User | View all interactive history | I can review my interaction history including my posts and other people's posts | - This allows users to review their interaction history - "Day-month-year" can be selected - Sort posts by day |  | 2 |  |  |  | 2 | 50
PB12 | Search the post | Personal User | Search the post | I can search for recent posts or posts I've missed | - This allows the user to search for the post username and search based on some keywords related to the post. - Approximate form search - Searching for special characters is not supported |  | 3 |  |  |  | 2 | 30
PB13 | View map in local area | Personal User | View map in local area | I can view a map of the local area where there are robbers to avoid | - Users cannot view maps in the local area if location access is not allowed |  | 1 |  |  |  | 4 | 200
PB14 | Login | Local Authority | Login to website | I can access my account | - If the information is valid, the user can login - If the wrong password is entered > 3 times, the user cannot log in to the system. |  | 3 |  |  |  | 2 | 30
PB15 | Log out | Local Authority | The ability to logout of the system | I can view login page | - User should be able to log out from anywhere of the website. |  | 3 |  |  |  | 2 | 30
PB16 | Edit account | Local Authority | Edit some new personal information in the account | I can change some personal information in my account | - A user cannot "submit" data without entering all the required fields |  | 3 |  |  |  | 2 | 30
PB17 | Verify user account | Local Authority | Censoring user registration accounts | I can authenticate the user's registered account | - Allow user's account authentication when registering an account |  | 2 |  |  |  | 3 | 40
PB18 | View the list of users | Local Authority | See all users list | I can manage all the user's lists | - Allow see the list of all users and allow delete and fix information |  | 3 |  |  |  | 3 | 30
PB19 | View the list of posts | Local Authority | See all user posts list | I can manage all user posts | - Allowed to see all posts of past and present |  | 2 |  |  |  | 2 | 50
PB20 | Verify the post | Local Authority | Moderate user post | I can moderate all user posts | - Click "confirm" button to browse the user's post and there will be a button that doesn't confirm the user's post |  | 2 |  |  |  | 3 | 40
Note on M7: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.1 | PB01 | Thiết kế UI đăng ký tài khoản | Long | Done | 3 | 3 | 0 | 5 | 2 | Day 2: 3
1.2 | PB01 | Xây dựng module kiểm tra tính hợp lệ các trường dữ liệu |  | Not started | 6 | 0 | 6 | 0 | -6
1.3 | PB01 | Develop CSS/HTML | Bình | Ongoing | 3 | 0 | 3 | 10 | 7
1.4 | PB01 | Lập trình | Bao | Done | 10 | 10 | 0 | 4 | -6 | Day 7: 10
1.5 | PB01 | Viết test case | Long | Done | 3 | 3 | 0 | 20 | 17 | Day 8: 3
1.6 | PB01 | Test & Fix | Jan | Ongoing | 3 | 0 | 3 | 0 | -3
1.7 | PB02 | Code & test |  | Not started | 20 | 0 | 20 | 0 | -20
1.8 | [5 empty] | 0 | 0 |  | 0
1.9 | [5 empty] | 0 | 0 |  | 0
1.1 | [5 empty] | 0 | 0 |  | 0
1.11 | [5 empty] | 0 | 0 |  | 0
1.12 | [5 empty] | 0 | 0 |  | 0
1.13 | [5 empty] | 0 | 0 |  | 0
1.14 | [5 empty] | 0 | 0 |  | 0
1.15 | [5 empty] | 0 | 0 |  | 0
1.16 | [5 empty] | 0 | 0 |  | 0
1.17 | [5 empty] | 0 | 0 |  | 0
1.18 | [5 empty] | 0 | 0 |  | 0
1.19 | [5 empty] | 0 | 0 |  | 0
1.2 | [5 empty] | 0 | 0 |  | 0
1.21 | [5 empty] | 0 | 0 |  | 0
1.22 | [5 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
|  |  |  | Total | 48 | 16 | 32 | 39 | -9 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 48 | 45 | 45 | 45 | 45 | 45 | 35 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
|  |  |  | Burn up | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Team member 1 | [16 empty] | 0
[8 empty] | Team member 2 | [16 empty] | 0
[8 empty] | Team member 3 | [16 empty] | 0
[8 empty] | Team member 4 | [16 empty] | 0
[8 empty] | Team member 5 | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2.1 | PB03 | Thiết kế UI đăng ký tài khoản | Long | Done | 3 | 3 | 0 | 5 | 2 | Day 2: 3
2.2 | PB03 | Xây dựng module kiểm tra tính hợp lệ các trường dữ liệu |  | Not started | 6 | 0 | 6 | 0 | -6
2.3 | PB03 | Develop CSS/HTML | Bình | Ongoing | 3 | 0 | 3 | 10 | 7
2.4 | PB03 | Lập trình | Bao | Done | 10 | 10 | 0 | 4 | -6 | Day 7: 10
2.5 | PB07 | Viết test case | Long | Done | 3 | 3 | 0 | 20 | 17 | Day 8: 3
2.6 | PB07 | Test & Fix | Jan | Ongoing | 3 | 0 | 3 | 0 | -3
2.7 | PB07 | Code & test |  | Not started | 20 | 0 | 20 | 0 | -20
2.8 | [5 empty] | 0 | 0 |  | 0
2.9 | [5 empty] | 0 | 0 |  | 0
2.1 | [5 empty] | 0 | 0 |  | 0
2.11 | [5 empty] | 0 | 0 |  | 0
2.12 | [5 empty] | 0 | 0 |  | 0
2.13 | [5 empty] | 0 | 0 |  | 0
2.14 | [5 empty] | 0 | 0 |  | 0
2.15 | [5 empty] | 0 | 0 |  | 0
2.16 | [5 empty] | 0 | 0 |  | 0
2.17 | [5 empty] | 0 | 0 |  | 0
2.18 | [5 empty] | 0 | 0 |  | 0
2.19 | [5 empty] | 0 | 0 |  | 0
2.2 | [5 empty] | 0 | 0 |  | 0
2.21 | [5 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
[6 empty] | 0 | 0 |  | 0
|  |  |  | Total | 48 | 16 | 32 | 39 | -9 | 0 | 3 | 0 | 0 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down | [5 empty] | 48 | 45 | 45 | 45 | 45 | 45 | 35 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
|  |  |  | Burn up | [5 empty] | 0 | 3 | 3 | 3 | 3 | 3 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Team member 1 | [16 empty] | 0
[8 empty] | Team member 2 | [16 empty] | 0
[8 empty] | Team member 3 | [16 empty] | 0
[8 empty] | Team member 4 | [16 empty] | 0
[8 empty] | Team member 5 | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms